## Tasks
Feel free to make ANY changes WITHOUT PERMISSION
ID | Threads | Tasks | Priority | Status | Assigned | CHECK THE "STRETCHGOALS" TAB too
| IMP | Important Things
| IMP-01 | Nothing, you have nothing to do as you've done everything. Just enjoy the calm after the storm.. :) | URGENT | In Prog. | All
THE FINAL STRAIGHT TO THE FINISH LINE
| END | BIGGEST ISSUES:
| END-01 | When you win the last level, no transition to a win screen | 0-BOSS | Done | Phil | <== didn't get the end game screen when I beat the game last time
| END-02 | Intro vids playing? | 0-BOSS | Done | Some1
| END-03 | Level selection menu issues? | 0-BOSS | Done | Phil
| END-04 | Level complete sound doesn't play | 0-BOSS | Done | Aik
| END-05 | In-game "quit menu" should take you to "Level Selection" | 1 | Done | Denes
| END-06 | Last balancing pass | 0-BOSS | Done | AlexS
| END-07 | UI communicate Tetris shape superpower? | 1
| END-07.1 | VFXs on Tetris shape superpower use | 3
| END-08 | Direction your character starts facing is wrong, should be facing towards the center | 1 | Done | Denes
| END-09 | LEVEL: 1-3: make it more difficult | 0-BOSS | Done | AlexS
| END-10 | LEVEL: key party: make it a bit more easy, more place to manoeuver and more freedom in some places, especially that last toxic source near the exit | 0-BOSS | Done | Phil
| END-11 | Hook Morty's last cinematic to the game: make it play when you click on the very first level | 0-BOSS | Done | Phil
| END-12 | SOUND: need to had some background sound to Morty's last vid (Or use existing music) | 0-BOSS | Done | Morty, AlexH
| END-13 | End game fade to black transition into end game screen | 1 | Done | Phil
| END-14 | UI: conveyor slides into the level on level start (currently is initialized with only "plus" signs, then switches) | 3
| END-15 | BLACK SCREEN: on level 1 vid | URGENT | Done | Denes
| END-16 | Level selection screen: "gray out" of locked level gone? | 0-BOSS | Done | Phil
LOCO | Core locomotion
LOCO-01 |  | Move around Interpolation | 0-MVP | Done | MattB
LOCO-02 |  | Turning around: when turning around, you should not move in that direction directly, unless you press down | URGENT | Done | Denes | <== after playtesting: this is needed (but only on hitting the key, not pressing down, in which case it should turn and move as it is now)
LOCO-03 |  | Turnign around: for the 180 turn specifically, ideally making it more "fluid" would be great | 0-MVP | Done | Denes
UNFOLD | Unfolding mechanics
UNFOLD-01 |  | Does the unfolding | 0-MVP | Done | MattB
UNFOLD-02 |  | Writes them into the grid | 0-MVP | Done | MattB
UNFOLD-03 |  | Animation integration | 0-MVP | Done | Denes
UNFOLD-04 |  | Rotating unfolded pattern depending on the direction | 0-MVP | Done | Maiko
UNFOLD-05 |  | Rotating shadow on the ground according to direction | 0-MVP | Done | Maiko
UNFOLD-06 |  | Hooking up animated character model to the grid character shape when spawn or respawn is called | 0-MVP | Done | Maiko
UNFOLD-07 |  | Choosing one unfold pattern for each Tetris shape | 1 | Done | Morty
UNFOLD-08 |  | Make the distinction between valid and invalid shadow preview more distinct (colour? fill? other?) | URGENT | Done | Denes
UNFOLD-09 |  | Tetris pieces superpower: unfolding ignores red toxic tile restriction | URGENT | Done. | Phil
UNFOLD-10 |  | Deployment restrictions: enable deploying on grass | URGENT | Done | Denes
UNFOLD-11 |  | Deployment restrictions: partial unfold (rest of unfold is wasted) | N/A |  |  | <== canned, as we don't allow partials now
UNFOLD-12 |  | Juice: VFX or camera shake or whatever when Tetris superpower unfold happens (to communicate "power" to the player) | 1
UNFOLD-13 |  | BUG: unfolding on grass doesn't always work (even though preview is green) | URGENT | Done | Phil
GRID | Grid movement limitations
GRID-01 |  | Grid creation | 0-MVP | Done | MattB
GRID-02 |  | Movement limitations [REQUIRES GD-07] | 0-MVP | Done | MattB
GRID-03 |  | Initial Preview Placement ("Shadow") | 0-MVP | Done | MattB
QUEUE | Conveyor Belt/Queue
QUEUE-01 |  | Game Design: conveyor/queue | 0-MVP | Done | AlexS
QUEUE-02 |  | UI Design: conveyor/queue | 0-MVP | Done | Vicky
QUEUE-03 |  | Programming: queue mode selection switch | 0-MVP | Done. | Maiko
QUEUE-04 |  | Programming: default queue "classic tetris - random piece" | 0-MVP | Done | Maiko
QUEUE-05 |  | Programming: Authored queue per level/scene | 0-MVP | Done. | Maiko
QUEUE-05.1 |  | Programming: "finite pieces mode" counter. If over: level over + death anim + "restart level" UI pop up | N/A |  | Maiko | <== canned, for now at least..
QUEUE-05.2 |  | Programming: if finite pieces mode then make "counter" so that UI can display pieces left | N/A |  | Maiko | <== canned, for now at least..
QUEUE-06 |  | Programming: authored queue "loop" mode: when arrive to end, restart loop | 0-MVP | Done. | Maiko
QUEUE-06.1 |  | authored queue "random" mode when finish (instead of ordered loop) | 2 | Done. | Maiko
QUEUE-07 |  | "Cycle" key/ability: can "sacrifice" piece to get next one (if limited queue. In random queue, just skip piece) | N/A |  |  | <== canned, for now at least..
QUEUE-08 |  | UI: make pattern in position 3 "appear" smoothly with a nice transition (turning visible + coming from left) | 1 | Done | Maiko
QUEUE-09 |  | UI: make icons in positions 2 and 3 slightly smaller, and growing up a bit when moving forward | 2 | Done. | Maiko
QUEUE-10 |  | UI: small "wobble" animation of shapes | 1 |  | Denes
QUEUE-11 |  | UI: slight curve on the queue ("rounding" the queue visually a bit) | 1
DATA | World building
DATA-01 |  | Level editor | 1 | Done | Phil
DATA-02 |  | Populate world with Art assets | 1 | Done | Aik, Phil
DATA-03 |  | Adjust environment according to generated level | URGENT | Done | Phil
DATA-04 |  | Base ground slightly offset in Y (Unity: z?) axis compared to grass (so that grass "sits on top of it") | 3
DATA-05 |  | Make "ground" extend further down | 1 | Done. | Phil&Matt
DATA-06 |  | Give side of ground cube some very basic "texture" (like: seing the lower layers of the ground) | 1 | N/A
DATA-07 |  | BUG: Level 12: Environments don't adjust correctly for 24x36 size level | 0-MVP | Done. | Phil&Matt
DATA-08 |  | Cubes starts not facing the best direction: make them face the "center", or "exit" | 1 | In Prog. | Denes
ANIM | Animation
ANIM-01 |  | cube model + animation | 0-MVP | Done | Mor&Vic
ANIM-02 |  | face animation | 0-MVP | Done | Mor&Vic
ANIM-03 |  | arms animation | 0-MVP | Done | Mor&Vic
ANIM-04 |  | Import animation into Unity | 0-MVP | Done | Mor&Vic
ANIM-05 |  | Level start anim (arriving into level, running up slightly inclined slope with slight rotation) | 1 | Done | Mor&Vic
ANIM-06 |  | Spawn anim (when new char spawns) | 1 | Done | Mor
ANIM-07 |  | Toxic spread animation (goes like this: "bloblboblboblbo") | 1 | Done | Mor
ANIM-08 |  | Create shape definitions for every remaining shape | 0-MVP | Done | AlexS
ANIM-09 |  | Valid/invalid tiles shadow preview more obvious (colours white/red? texture? animation? other?) | URGENT | Done | Denes
ANIM-10 |  | Character colours | 0-MVP | Done | Denes
ANIM-11 |  | Grass animation: animation | 2 | Done | Mor&Vic
ANIM-12 |  | Grass animation: code | 1 | In Prog. | Aik, Phil
ANIM-13 |  | Flower animations and slight wobble | 2
ANIM-14 |  | Partial unfold animation (if you make partial unfold and rest is wasted) | N/A |  |  | <== canned, as we don't allow partials now
ANIM-15 |  | Grass VFX when walking on it: grass blades flying all over the place | 2
ANIM-16 |  | Colour on unfolding anim characters | 2 | Done | Denes
ANIM-17 |  | Juice: Anim for toxics being removed | 3
ANIM-18 |  | Juice: Unfolding: Unfolded piece stays a "tiny bit" (0.25 sec?) longer on the ground (so you can see shape a bit longer) | 3 | Done | Denes
ANIM-19 |  | Toxic: make it less "right angle", a bit more soft edges | 2
ANIM-20 |  | Change the "exit" pink light to something better, such as god's ray | 2 | Done | Denes
ANIM-21 |  | Programming: level tiles all flip to grass when reach exit (in a domino effect way, not all at once) | 2
ANIM-22 |  | Turning around: quick 180 turn around (without move) for when you just tap the key [for LOCO-02] | 1 | Done | Denes
REND | Rendering
REND-01 |  | Unlit w Shadow | 0-MVP | Done | Maiko
REND-02 |  | Decrease shadow strength | 0-MVP | Done | Denes
REND-03 |  | Decrease light level | 0-MVP | Done | Denes
CAM | Camera
CAM-01 |  | Initial camera | 0-MVP | Done | MattB
CAM-02 |  | Final camera setup: design (i.e. smooth zoom out when idle, zoom in when moving etc…) | 1 | Done
CAM-03 |  | Final camera setup: implementation | 1 | Done
CAM-04 |  | Camera travelling: from unfolded character to new spawn (smooth travel) | 1 | Done | Denes
CAM-05 |  | Camera travelling: on level intro: travel to exit, zoom out, then travel back to first char | 1 | Done
LVL | Level Design
LVL-01 |  | Test level integration | 0-MVP | Done | Aik
LVL-02 |  | Design: Tutorial levels 1, 2, 3.. | 0-MVP | Done | AlexS
LVL-02.1 |  | Implementation: Tutorial levels 1, 2, 3.. | 0-MVP | Done | Phil
LVL-02.2 |  | Insert tutorial level before level 2 with just simple go around walls (or take shortcut) | URGENT | Done | AlexS
LVL-03 |  | Main level 1 | URGENT | Done | AlexS
LVL-03.1 |  | Main level 2 | URGENT | Done | AlexS
LVL-04 |  | Gather ideas for cool level design [requires playing test level first] | 1 | Done | All
LVL-05 |  | Implementation of most interesting levels | URGENT | Done | AlexS
LVL-06 |  | "Boss" level (win conditions) | URGENT | Done | AlexS
LVL-07 |  | Tutorial levels: scripts for tutorial text when you step on them (pop out small text in top corner or .png?) | 2
LVL-08 |  | Post-Boss level: infinite sandbox levels with procedural + RNG queue | 3
LVL-09 |  | Feedback session on level design, gather feedback | 0-MVP | In Prog. | AlexS
LVL-10 |  | Iterate on levels with feedback | 0-MVP | In Prog. | AlexS
LVL-11 |  | Make levels 12, 24, or 26 | 0-MVP | Done | AlexS
LVL-12 |  | Make "Key" level | 0-MVP | Done | Phil
LVL-13 |  | Adjust level naming [after LVL-12 task is complete] | 0-MVP | Done | Phil
LVL-14 |  | END GAME: last "exit" tile sends you to a credits screen, and button there sends you to level selection | 0-MVP
STORY | Story telling
STORY-01 |  | Nature vs Toxic, healing the toxic wasteland | 1 | Done | All
STORY-02 |  | Design the game name | 2 | Done | Morty
STORY-03 |  | Basic Intro, a picture with text
STORY-04 |  | Basic Ending
GD | Game Design
GD-01 |  | Initial Core Loop | 0-MVP | Done | AlexS
GD-02 |  | Initial Player Goals | 0-MVP | Done | AlexS
GD-03.1 |  | Formalize list of shapes - Cubes | 1 | Done | AlexS
GD-03.2 |  | Formalize list of shapes - Tetris shapes | 1 | Done | AlexS
GD-04 |  | Iterate core game loop and player goals | 1 | Done | All
GD-04.1 |  | Iterate core game loop and player goals - round 2 | 2 | Done | AlexS
GD-05 |  | Game over condition design | 0-MVP | Done | AlexS
GD-05.1 |  | Game over condition integration | 0-MVP | Done | Unsung Hero
GD-06 |  | Toxic spread game design effect on other tiles | N/A
GD-07 |  | Movement restrictions: overlapping, terrain type, walking restrictions etc.. | N/A
GOD | Making an entire and fully playable second game on the side
GOD-01 |  | Make Blues Brothers game | URGENT | In Prog. | Denes
GOD-02 |  | Get sued for copyright | URGENT | In Prog. | Denes | lol
GOD-03 |  | Submit it as a second game (DO IT) | URGENT | In Prog. | Denes
ENV | Environment
ENV-01 |  | General environment assets, props (3 levels) | 0-MVP | In Prog. | MattG
ENV-02 |  | Environment 24x24 | 0-MVP | Done | MattG
ASS | Assets
ASS-01 |  | Rock (many...rocks) | 1 | Done | MattG
ASS-01.1 |  | Moar rocks! Variations, dead wood trees, dead tree trunk, boulders, others etc.. | 2
ASS-02 |  | Ground textures/colours | 0-MVP | Done
ASS-03 |  | Toxic Waste VFX | 1 | Done | Mor
ASS-03.1 |  | Toxic VFX 2 | 1 | Done | Aik
ASS-04 |  | Toxic Ground | 1 | Done
ASS-05 |  | Entrance & exit assets | 0-MVP |  |  | <== do we still need these? Can these be integrated with the world gen.?
ASS-06 |  | Programming: stitching toxic tiles from their sides according to logic | 0-MVP |  | Aik
ASS-07 |  | Differentiating "red" and "yellow" toxic tiles (colour? texture? pattern? shape? other?) | URGENT | Done | Aik
UI | User Interface
UI-01 |  | Start Menu functional implementation | 0-MVP | Done | AlexS |  | START MENU: NEED TO ADD FOLLOWING:
UI-02 |  | In-game menu functional implementation | 0-MVP | Done | Denes |  |  |  | controls (not reassigning controls, just displaying them)
UI-03 |  | Start Menu Art | 1 | Done | Vic |  |  |  | sound control
UI-04 |  | In-game menu art | 1 | Done | Vic |  |  |  | change camera view: iso/perspective (stretch goal)
UI-05 |  | Art/UI: Game menu icons using tetris shapes | 1 | Done | Mor&Vic |  |  |  |  | Use two screenshots to illustrate both options
UI-04.1 |  | Level Selection menu art | 1 | In Prog. | Vic
UI-04.2 |  | Level Complete Art (Win!) | 1 | Done | Mor&Vic |  | IN-GAME MENU: DESIGN:
UI-05 |  | End-game art | 1 | In Prog. | Vic |  |  |  | resume | Done | Denes
UI-06 |  | Title Logo - UNFOLD - Band of Boxes | 1 | Done | Mor&Vic |  |  |  | exit game
UI-06 |  | Conveyor belt: small patterns hand-drawn (11 cubes patterns + 4 tetris patterns) | 0-MVP | Done | Mor&Vic |  |  |  | main menu | Done | Denes
UI-07 |  | UI Polish: Start Menu | 1 | In Prog. | Denes |  |  |  | controls (not reassigning controls, just displaying them)
UI-08 |  | UI Polish: In-game Menu | 1 | In Prog. | Denes |  |  |  | restart level | Done | Denes
UI-09 |  | Start Menu: hook the music in | 0-MVP | In Prog. | Aik |  |  |  | sound control
UI-10 |  | Assign the right UI shape to the ShapeDefinitions | 0-MVP | Done | Denes |  |  |  | change camera view: iso/perspective (stretch goal)
UI-11 |  | UI: counter for how many pieces you have left in finite pieces mode | N/A |  | Mor&Vic | <== canned, for now at least.. (sorry!) |  |  |  | Use two screenshots to illustrate both options
UI-12 |  | Sound volume control in start menu | 1 |  |  |  |  | EFFECTS NEEDED FOR IN-GAME MENU:
UI-13 |  | Sound volume control in in-game menu | 1 | [5 empty] | Game pauses | Done | Denes
UI-14 |  | UI draft: test if putting a face on "current" piece in queue works visually or not | 1 |  | Vicky |  |  |  | Background dark filter
UI-15 |  | Cool team logo | 1 | [5 empty] | Game music stops (or temp. reduced to like 10% of current value)
UI-16 |  | Credits screen design: one tetris character per team member? | 3
UI-17 |  | Level restart button in in-game menu | 1 | Done | Denes
UI-18 |  | Display level name upon entering level | 3 | Done
UI-19 |  | UI: communicating that Tetris pieces are more powerful: UI glows? Shape shakes? Something else? | 1
UI-20 |  | UI: upon reaching end level, "continue" button appears below the "level complete" | 1 | Done | Denes
UI-21 |  | Replace game retail file logo with something else | 3
SOUND | Sound and Music:
SOUND-01 |  | Prototype music | 0-MVP | Done | AlexH
SOUND-01.1 |  | - 2 tracks, grim => bright | 1 | Done | AlexH
SOUND-01.2 |  | - more tracks for layering, polishing so we can distiguish the different from each tones | 1 |  | AlexH
SOUND-02 |  | Sound effects | 0-MVP | Done | AlexH
SOUND-02.1 |  | - footstep | 1 | Done | AlexH
SOUND-02.2 |  | - toxic waste | 1 | Done | AlexH
SOUND-02.3 |  | - toxic spread | 1 | Done | AlexH
SOUND-02.4 |  | - UI: some bubbly | 1 | Done | AlexH
SOUND-02.5 |  | - Burn sound effect | 2 | Done | AlexH
SOUND-02.6 |  | - Unfolding sound (separate) | 1 | Done | AlexH
SOUND-03 |  | Multi layering music in Unity | 1 | Done | AlexH
SOUND-04 |  | Voice acting | 1 | Done | AlexH
SOUND-05 |  | Industrial level sound | 2 | Done | AlexH
SOUND-06 |  | Desert level sound | 2 | Done | AlexH
SOUND-07 |  | Integrate audio_test project files to the avocado unity project | 0-MVP | Done | AlexH
SOUND-08 |  | Menu theme music: something that evokes the other themes/levels or rhymes with them, more calm | 1 | Done | AlexH
SOUND-09 |  | Integration: Hooking sound files into the game | 0-MVP | In Prog. | Denes
SOUND-10 |  | Sound for "partial unfold" on toxic (starts as unfold sound then burning or acid sound) | N/A
SOUND-11 |  | Sound for "partial unfold" on rock (starts as unfold sound then crashing/breaking on a rock wall) | N/A |  |  | <== canned, as we don't allow partials now
SOUND-12 |  | End of level short sounds/music | 1 | Done
SOUND-13 |  | Invalid unfold sound when you press space while the preview is red | 1 | Done | AlexH
SOUND-14 |  | Integration: Hook Up Toxic Waste Expand SFX | 2 | In Prog. | Aik
SOUND-15 |  | Integration: Hook Up Toxic Waste Loop SFX | 2 | In Prog. | Aik
SOUND-16 |  | Integration: Hook Up Level Load SFX | 2
SOUND-17 |  | Integration: Hook Up Invalid Unfold SFX | 2
SOUND-18 |  | Integration: Hook Up Front End Music | 2
SOUND-19 |  | Integration: Hook Up UI Pause Menu SFX | 2
SOUND-20 |  | Hook up last bits of audio to pause menu etc | 2

## StretchGoals
Feel free to make ANY changes WITHOUT PERMISSION
ID | Threads | Tasks | Priority | Status | Assigned | COPY FROM HERE INTO TASKS IF YOU WANT TO ADD THEM
LOCO | Core locomotion
UNFOLD | Unfolding mechanics
GRID | Grid movement limitations
QUEUE | Conveyor Belt/Queue
|  | Programming: authored queue mode: ability to "insert" a piece in the queue (with things you find in the level) | CANNED | In progress | Maiko
Programming: random queue mode: ability to restrict random selection to a list of pieces (per level)
DATA | Database Interface: state encoding
Write
Read
Online leaderboard
WORLD | World Building
Smooth level transition: world is built around character when transitioning between levels
People can submit their own levels, or custom build
ANIM | Animation
2nd character face
God ray or glowing animation VFX for Exit or Entry doors etc
REND | Rendering
Juice the fuck out of the game: God Rays, AAA shaders, shiny effects and stuff
CAM | Camera
Option in game menus: orthographic camera
Smooth out level transition (light dimming effect with superimposed gray or dark filter)
LVL | Level Design
Procedural level generation
GD | Game Design
Level scoring: counting points for completed levels: design
Level scoring: counting points for completed levels: implementation
ENV | Environment
ASS | Assets
Level entrance & exit that are not on the side but can be placed anywhere
UI | User Interface
Level selection screen: graying out levels that you haven't unlocked yet
SOUND | Sound and Music:
Story telling
cut scenes

## ShapePatterns
CUBE Patterns | [32 empty] | "I may look boring, but inside…I'm beautiful!"
Impl. Prio: |  |  |  | 0-MVP |  |  |  |  | 0-MVP | [5 empty] | 1 |  |  |  |  | 1 |  |  |  |  | 1 | [5 empty] | 1
Cute name: |  |  |  | Cross |  |  |  |  | T-shape | [5 empty] | Boomerang |  |  |  |  | Lockpick |  |  |  |  | Key | [5 empty] | S-shape
|  |  |  | 3, 2 |  |  |  | 4, 3 | 3, 2 | 5, 3 | [5 empty] | 5, 4 |  |  | 5, 4 | 4, 3 |  |  |  |  | 5, 3 | [5 empty] | 4, 3 | 5, 4
Pattern: |  |  | 4, 2 | 2, 1 | 5, 2 |  |  |  | 2, 1 | [5 empty] | 3, 2 | 4, 3 |  |  |  | 3, 1 |  |  |  | 4, 3 | 3, 1 | [5 empty] | 3, 2
|  |  |  | 1, 0 |  |  |  |  | 1, 0 | [5 empty] | 2, 0 |  |  |  |  | 1, 0 | 2, 1 |  |  |  | 1, 0 | 2, 1 |  |  |  |  | 2, 0
|  |  |  | 0, 0 |  |  |  |  | 0, 0 |  |  |  |  | 1, 0 | 0, 0 |  |  |  |  | 0, 0 |  |  |  |  | 0, 0 |  |  |  |  | 1, 0 | 0, 0
Player (facing up):
Coordinates: |  |  |  | 0,4 |  |  |  | -1,4 | 0,4 | 1,4 | [5 empty] | 1,4 |  |  | -1,4 | 0,4 |  |  |  |  | 0,4 | [5 empty] | 0,4 | 1,4
|  |  | -1,3 | 0,3 | 1,3 |  |  |  | 0,3 | [5 empty] | 0,3 | 1,3 |  |  |  | 0,3 |  |  |  | -1,3 | 0,3 | [5 empty] | 0,3
|  |  |  | 0,2 |  |  |  |  | 0,2 | [5 empty] | 0,2 |  |  |  |  | 0,2 | 1,2 |  |  |  | 0,2 | 1,2 |  |  |  |  | 0,2
|  |  |  | 0,1 |  |  |  |  | 0,1 |  |  |  |  | -1,1 | 0,1 |  |  |  |  | 0,1 |  |  |  |  | 0,1 |  |  |  |  | -1,1 | 0,1
|  |  |  | 0,0 |  |  |  |  | 0,0 | [5 empty] | 0,0 |  |  |  |  | 0,0 |  |  |  |  | 0,0 | [5 empty] | 0,0
Impl. Prio: |  |  |  | 1 |  |  |  |  | 1 | [5 empty] | 1 |  |  |  |  | 1 |  |  |  |  | 1
Cute name: |  |  |  | Gun |  |  |  |  | Braid | [5 empty] | Axe |  |  |  |  | Dab |  |  |  |  | Worm
5, 4
|  |  |  | 4, 2 | 5, 4 |  |  |  |  | 5, 4 |  |  |  | 5, 4 |  |  |  |  | 5, 4 | [6 empty] | 4, 3
Pattern: |  |  | 3, 2 | 2, 1 |  |  |  |  | 3, 2 | 4, 3 |  |  |  | 4, 3 | 3, 1 |  |  |  | 4, 2 | 2, 1 | 3, 2 |  |  |  | 2, 1 | 3, 2
|  |  |  | 1, 0 |  |  |  | 1, 0 | 2, 1 | [5 empty] | 1, 0 | 2, 1 |  |  |  | 1, 0 |  |  |  |  | 1, 0
|  |  |  | 0, 0 |  |  |  | 0, 0 | [6 empty] | 0, 0 |  |  |  |  | 0, 0 |  |  |  |  | 0, 0
Player (facing up): | [33 empty] | -3, 8 | -2, 8 | -1, 8 | 0, 8 | 1,8 | 2, 8 | 3, 8
[26 empty] | 1,5 | [7 empty] | -3, 7 | -2, 7 | -1, 7 | 0, 7 | 1,7 | 2, 7 | 3, 7
Coordinates: |  |  |  | 0,4 | 1,4 |  |  |  |  | 2,4 |  |  |  | -1,4 |  |  |  |  | -1,4 | [5 empty] | 0,4 | 1,4 | [7 empty] | -3, 6 | -2, 6 | -1, 6 | 0, 6 | 1,6 | 2, 6 | 3, 6
|  |  | -1,3 | 0,3 |  |  |  |  | 1,3 | 2,3 |  |  |  | -1,3 | 0,3 |  |  |  | -1,3 | 0,3 | 1,3 |  |  |  | 0,3 | 1,3 | [7 empty] | -3, 5 | -2, 5 | -1, 5 | 0, 5 | 1,5 | 2, 5 | 3, 5
|  |  |  | 0,2 |  |  |  | 0,2 | 1,2 | [5 empty] | 0,2 | 1,2 |  |  |  | 0,2 |  |  |  |  | 0,2 | 1,2 | [7 empty] | -3, 4 | -2, 4 | -1, 4 | 0,4 | 1,4 | 2, 4 | 3, 4
|  |  |  | 0,1 |  |  |  | 0,1 | [6 empty] | 0,1 |  |  |  |  | 0,1 |  |  |  |  | 0,1 | 1,1 | [7 empty] | -3, 3 | -2,3 | -1, 3 | 0,3 | 1,3 | 2, 3 | 3, 3
|  |  |  | 0,0 |  |  |  | 0,0 | [6 empty] | 0,0 |  |  |  |  | 0,0 |  |  |  |  | 0,0 | [8 empty] | -3, 2 | -2, 2 | -1, 2 | 0,2 | 1,2 | 2, 2 | 3, 2
[34 empty] | -3, 1 | -2, 1 | -1, 1 | 0,1 | 1,1 | 2, 1 | 3, 1
0,0
TETRIS shapes
Impl. Prio: |  |  |  | 1 | [7 empty] | 1 | [8 empty] | 1 | [6 empty] | 1
Shape:
Cute name: |  |  |  | Line/Plus sign | [7 empty] | Small-T/Skullface | [8 empty] | L-shape/Antenna | [6 empty] | Z-shape/Firework
|  |  |  | 7-6 | [21 empty] | 17,16
|  |  |  | 6-5 | [21 empty] | 16,14 | 12,9 | 13,12 | 11,10
|  |  |  | 5-4 | [6 empty] | 16,13 | 13,10 | 17,13 | [12 empty] | 14,9 | 9,6 | 6,5 | 10,8
|  |  |  | 4-3 | [5 empty] | 14,11 |  | 10, 7 |  | 15,12 |  |  | 13,11 | 11,10 | 10,8 | 12,10 | [5 empty] | 15,14 | 7,5 | 5,4 | 8,5
Pattern: | 13-12 | 12-11 | 11-3 | 3-2 | 8-3 | 9-8 | 10-9 |  |  | 11,8 | 8, 5 | 7, 4 | 9, 6 | 12,9 |  |  |  |  | 8,6 |  | 3,2 |  | 9,7 |  |  |  |  | 4,3
|  |  |  | 2-1 | [6 empty] | 5, 2 | 4, 1 | 6, 3 | [5 empty] | 6,4 | 4,2 | 2,1 | 5,2 | 7,5 |  |  |  |  | 3,2
|  |  |  | 1-0 | [6 empty] | 2, 1 | 1, 0 | 3, 1 | [7 empty] | 1,0 | [5 empty] | 1,0 | 2,1
|  |  |  | 0-0 | [7 empty] | 0, 0 | [8 empty] | 0,0 | [5 empty] | 0,0
Player (facing up): | [6 empty] | 14 | [6 empty] | 18 | [8 empty] | 14 | [5 empty] | 18
Coordinates: | [25 empty] | -1, 8
|  |  |  | 0, 7 | [6 empty] | -1, 7 | 0, 7 | 1,7 | [12 empty] | -1, 7 | 0, 7 | 1,7 | 2, 7
|  |  |  | 0, 6 | [5 empty] | -2, 6 |  | 0, 6 |  | 2, 6 | [11 empty] | -1, 6 | 0, 6 | 1,6 | 2, 6
|  |  |  | 0, 5 | [5 empty] | -2, 5 | -1, 5 | 0, 5 | 1,5 | 2, 5 |  |  | -4, 5 | -3, 5 | -2, 5 | -1, 5 | [6 empty] | 0, 5 | 1,5 | 2, 5
| -3, 4 | -2, 4 | -1, 4 | 0,4 | 1,4 | 2, 4 | 3, 4 |  |  | -2, 4 | -1, 4 | 0,4 | 1,4 | 2, 4 |  |  |  |  | -2, 4 |  | 0,4 |  | 3, 3 |  |  |  |  | 1,4
|  |  |  | 0,3 | [5 empty] | -2,3 | -1, 3 | 0,3 | 1,3 | 2, 3 |  |  |  |  | -2,3 | -1, 3 | 0,3 | 1,3 | 2, 3 |  |  |  | 0,3 | 1,3
|  |  |  | 0,2 | [6 empty] | -1, 2 | 0,2 | 1,2 | [7 empty] | 0,2 | [5 empty] | 0,2 | 1,2
|  |  |  | 0,1 | [7 empty] | 0,1 | [8 empty] | 0,1 | [5 empty] | 0,1
|  |  |  | 0,0 | [7 empty] | 0,0 | [8 empty] | 0,0 | [5 empty] | 0,0

## BugSmashlist
Core locomotion
Unfolding mechanics
Grid movement limitations
Conveyor Belt/Queue
Database Interface: state encoding
Animation
Rendering
Level Design
[ENVIRONMENT] Environment is too close for level 2... the exit is lost under the rear rock wall.
[ENVIRONMENT] The ground tile intersects with the toxic pits to make them look like dirt.
Game Design
Environment
Toxic Pits disappear when some of the surrounding waste has been cleared
Assets
User Interface
| Start Menu Background image stretch issue | AlexS
| In game menu: ESC key script: make it work | AlexS
| Verify "exit game" works in standalone builds | AlexS
UI: queue has magnifier
Sound and Music:
Story telling

## GDissues
Game Design issues to resolve:
As you advance, it takes longer to return to your latest position. What can we do to make this interesting?
Hazards, invading the road?
Should we allow overlapping unfolded areas?
If we do, then, too easy
Need to restrict how many shapes you have
If we don't allow, then, a bit too restrictive in cramped areas
Then, what?
Probably better to not allow deployment on grass as it will let us craft levels
Otherwise too unpredictable
Should big shapes do something extra?
Probably should ignore some restrictions, such as toxic restrictions
Observation: this game doesn't scale well with increasing level size, because you respawn further and further each time

## Levels
Tutorial
Level builder how to use:
| Things we need the player to be able to do: | [13 empty] | Things we need the player to feel:
It can be run from the Grid3 scene if you want to test
| GAMEPLAY | [12 empty] | NARRATIVE | [18 empty] | When you start the scene you'll need to press the 'Home' key to spawn the level layout
The layout itself is read from a csv file
| Level 1 | [31 empty] | We can author new levels by creating an Excel sheet and inputting numbers from 0 - 5:
|  | Move | [12 empty] | Something's going on the other side | [18 empty] | 0 - Empty (unset tile)
|  | Deploy | [12 empty] | Toxic not yet visible, dirt soil, with just a few cells to cover | [18 empty] | 1 - Start tile
|  | Can and can't deploy zones | [12 empty] | Reach other side | [18 empty] | 2 - End tile
|  | Make a path and reach the goal | [31 empty] | 3 - Magma/Toxic tile
4 - Blocking (rocks) tile
| Level 2 | [32 empty] | 5 - Solid ground (pre-gen island)
|  | Deploy a specific pattern | [12 empty] | See that there's toxic everywhere | [17 empty] | If you make any levels you should save them to Assets/Resources/Levels/Lv#.txt
|  | Cover a hazard | [12 empty] | Need specific shape to pass through narrow gap | [17 empty] | Where # is the level number
|  | Covering all Hazards makes the exit available | [12 empty] | Need to cover hazards, exit lights up after that | [17 empty] | Also, yes they need to be .txt files because of Unity reasons
Edit the text file and remove any trailing blank lines
Level 3
|  | "Hazards can grow" | [12 empty] | Toxic waste covers exit, need to clean up | [18 empty] | 0 | Empty (unset tile)
|  | Toxic zone can be reduced | [12 empty] | Need to cover up to the hazard source | [18 empty] | 1 | Start tile
|  | Hazards can be covered | [12 empty] | Clean and exit | [18 empty] | 2 | End tile
[15 empty] | Outro and msg: "we have to do something about this shit!" | [18 empty] | 3 | Magma/Toxic tile
[34 empty] | 4 | Blocking (rocks) tile
12x24 | [33 empty] | 5 | Solid ground (pre-gen island)
0 | 0 | 0 | 4 | 5 | 5 | 5 | 2 | 5 | 5 | 5 | 4
0 | 0 | 4 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | [12 empty] | Lv1 |  | Tutorial 0: "Square One"
0 | 4 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 0 | 4
0 | 4 | 0 | 4 | 0 | 0 | 5 | 5 | 5 | 0 | 0 | 4 | [14 empty] | Patterns allowed: | [6 empty] | T-shape |  |  |  |  | Braid |  |  |  | Worm | [5 empty] | GAMEPLAY |  |  |  |  | NARRATIVE
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | [36 empty] | Level 0
4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | [37 empty] | Move |  |  |  |  | Let's cover a surface
4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | [37 empty] | Deploy
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | [15 empty] | Reasons:
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | [16 empty] | Good for covering all sides
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | [16 empty] | And also an easily distinguishable variation
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | [15 empty] | Goal: just make them move and deploy a their own pace
5 | 5 | 5 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 4 | [17 empty] | give them some space
1 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | [15 empty] | Options: |  |  |  | Queue type: |  |  |  |  | Authored
5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | [19 empty] | Loop/Finite: |  |  |  |  | Loop
0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | [19 empty] | Authored queue: |  |  |  |  | 1 | Braid
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | [24 empty] | 2 | T-Shape
0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 4 | 4 | 4 | [24 empty] | 3 | Worm |  |  |  | … | (loop)
0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 0
4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0
4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0
12x24
4 | 5 | 2 | 5 | 5 | 4 | 5 | 4 | 4 | 4 | 0 | 4
5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 4 | 4 | 0 | [12 empty] | Lv2 |  | Tutorial 1: "Winding Roads"
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | [14 empty] | Patterns allowed: | [6 empty] | Braid |  |  |  | Axe |  |  |  | Worm |  |  |  |  | T-shape
4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 4 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0
4 | 4 | 0 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0
4 | 4 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0
4 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 0 | 4 | [14 empty] | Options:
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4
4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | [17 empty] | Queue type: |  |  |  |  | Authored
4 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [17 empty] | Loop/Finite: |  |  |  |  | Loop
4 | 0 | 0 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | [17 empty] | Authored queue: |  |  |  |  | 1 | Braid
0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | [22 empty] | 2 | T
0 | 4 | 4 | 4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [22 empty] | 3 | Worm
5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | [22 empty] | 4 | Axe
1 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 4 | [22 empty] | … | (loop)
5 | 5 | 5 | 4 | 5 | 5 | 4 | 0 | 0 | 0 | 4 | 4
4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
12x24
4 | 0 | 5 | 5 | 5 | 2 | 5 | 5 | 5 | 0 | 4 | 4
4 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 4 | 0 | [12 empty] | Lv3 |  | Tutorial 2: "Obstacles"
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4
0 | 4 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | [14 empty] | Patterns allowed: | [6 empty] | Cross |  |  |  |  | Lockpick |  |  |  |  | Gun |  |  |  |  | GAMEPLAY | [11 empty] | NARRATIVE
4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | [36 empty] | Level 1
0 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | [37 empty] | Move | [11 empty] | Something's going on the other side
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | [37 empty] | Deploy | [11 empty] | Toxic not yet visible, dirt soil, with just a few cells to cover
4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | [37 empty] | Can and can't deploy zones | [11 empty] | Reach other side
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | [37 empty] | Make a path and reach the goal
4 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | [16 empty] | Reasons:
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | [17 empty] | Good to have an easily recognizable shape
0 | 4 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 4 | 4 | [17 empty] | And also an easily distinguishable variation
4 | 0 | 4 | 0 | 0 | 5 | 0 | 0 | 0 | 4 | 4 | 0 | [16 empty] | Goal: make them deploy and use patterns purposefully
0 | 0 | 0 | 0 | 5 | 5 | 5 | 0 | 0 | 4 | 0 | 4
4 | 0 | 0 | 0 | 5 | 5 | 5 | 0 | 0 | 4 | 4 | 0 | [15 empty] | Options:
0 | 0 | 0 | 0 | 5 | 5 | 5 | 0 | 4 | 4 | 0 | 4
0 | 5 | 5 | 0 | 0 | 5 | 0 | 0 | 4 | 0 | 0 | 0 | [18 empty] | Queue type: |  |  |  |  | Authored
1 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 4 | 4 | 0 | 4 | [18 empty] | Loop/Finite: |  |  |  |  | Loop
0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | [18 empty] | Authored queue: |  |  |  |  | 1 | Cross
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | [23 empty] | 2 | Lockpick
4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 0 | 0 | [23 empty] | 3 | Gun
4 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 0 | 4 | 0 | [23 empty] | … | (loop)
4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0
12x24
4 | 4 | 0 | 5 | 2 | 5 | 0 | 0 | 4 | 0 | 4 | 4
4 | 0 | 0 | 5 | 5 | 5 | 0 | 0 | 0 | 4 | 0 | 4 | [12 empty] | Lv4 |  | Tutorial 3: "Hazards"
0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4
0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 4 | [14 empty] | Patterns allowed: | [6 empty] | Boomerang |  |  |  | Key |  |  |  | S-shape |  |  |  | Axe |  |  |  | Dab |  | GAMEPLAY | [12 empty] | NARRATIVE
0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | [39 empty] | Level 2
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | [40 empty] | Deploy a specific pattern | [12 empty] | See that there's toxic everywhere
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | [40 empty] | Cover a hazard | [12 empty] | Need specific shape to pass through narrow gap
4 | 0 | 5 | 5 | 5 | 0 | 0 | 4 | 4 | 4 | 0 | 0 | [40 empty] | Covering all Hazards makes the exit available | [12 empty] | Need to cover hazards, exit lights up after that
0 | 0 | 5 | 5 | 5 | 0 | 0 | 0 | 4 | 0 | 0 | 4
0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 0 | [16 empty] | Reason:
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | [17 empty] | Rest of the crew
4 | 0 | 0 | 3 | 0 | 0 | 0 | 4 | 4 | 4 | 0 | 0 | [17 empty] | Introduce toxic
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | [16 empty] | Queue type: |  |  |  |  | Authored | [6 empty] | Toxic Speed: | [5 empty] | 20
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | [16 empty] | Loop/Finite: |  |  |  |  | Loop | [6 empty] | Toxic Spread: | [5 empty] | 10
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | [16 empty] | Authored queue: |  |  |  |  | 1 | Key | [5 empty] | Max Spread: | [5 empty] | 4
0 | 0 | 0 | 5 | 0 | 0 | 0 | 4 | 4 | 0 | 4 | 0 | [21 empty] | 2 | S-Shape
0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 4 | [21 empty] | 3 | Axe
0 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | [21 empty] | 4 | Dab
1 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | [21 empty] | 5 | Boomerang
0 | 5 | 5 | 5 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | [21 empty] | … | (loop)
0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 4
24x24
0 | 4 | 4 | 4 | 4 | 4 | 0 | 5 | 5 | 5 | 5 | 2 | 5 | 5 | 5 | 5 | 0 | 4 | 4 | 4 | 4 | 0 | 0 | 0 |  | Lv5
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 |  |  | Tutorial 4: "TOXIC BAND"
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 4
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  |  | Patterns allowed: | [5 empty] | Cross |  |  |  |  | Lockpick |  |  |  | Worm | [6 empty] | GAMEPLAY | [11 empty] | NARRATIVE
0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | [24 empty] | Level 3
4 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 4 | 0 | [25 empty] | "Hazards can grow" | [11 empty] | Toxic waste covers exit, need to clean up
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | [25 empty] | Toxic zone can be reduced | [11 empty] | Need to cover up to the hazard source
4 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | [25 empty] | Hazards can be covered | [11 empty] | Clean and exit
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 0 | [25 empty] | Tetris pieces | [11 empty] | Outro and msg: "we have to do something about this shit!"
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 4
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 0
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | [8 empty] | Line/Plus sign | [8 empty] | Small-T/Skullface | [9 empty] | REQUIRES: should give you a extra text msg when you receive a big piece:
0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | [28 empty] | "this piece is more efficient against toxic"
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 4
0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | [24 empty] | Queue type: |  |  |  | Authored | [11 empty] | Toxic Speed: |  |  |  | 15
4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | [24 empty] | Loop/Finite: |  |  |  | Loop | [11 empty] | Toxic Spread: |  |  |  | 10
0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | [24 empty] | Authored queue: |  |  |  | 1 | Cross |  |  |  | 6 | Lockpick | [5 empty] | Max Spread: |  |  |  | 5
0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | [28 empty] | 2 | Lockpick |  |  |  | 7 | Worm
4 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | [28 empty] | 3 | Worm |  |  |  | 8 | Skullface
0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | [28 empty] | 4 | Plus |  |  |  | … | (loop)
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | [28 empty] | 5 | Cross
4 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0
4 | 4 | 4 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 1 | 5 | 5 | 5 | 5 | 5 | 0 | 4 | 4 | 4 | 0 | 0 | 0
Main Levels
Level Ideas:
First 3 levels:
[31 empty] | Start in the middle of Toxic, you have to clear to reach the exit | [21 empty] | "Tower defense": straighforward level: fast expanding toxics on one side, you on the other, who will win? (toxic of course)
[5 empty] | GAMEPLAY | [12 empty] | NARRATIVE | [13 empty] | Requires: entrance in the middle of the level | [20 empty] | Scattered rocks all over the place
[31 empty] | Unfold Royale: start the entire perimeter toxic and growing inwards, shrinking =o] | [21 empty] | Have dedicated levels for each shape as an introduction to each shape
[31 empty] | Can we make a level with no unfolding? | [21 empty] | Have a level with limited pieces
[32 empty] | Like: labyrnth, or racing against expanding toxic (fast one) | [20 empty] | Have a "tricky" level, where you have to go through several small areas
Evil reincarnation : you unfold into Toxic
24x24
4 | 0 | 4 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 4 | 0 | 4 |  | Lv6
0 | 4 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 4 | 0 |  |  | Main 1-1: "STONE FOREST RUN"
4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4
0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Patterns allowed: | [6 empty] | Braid |  |  |  | Axe |  |  |  | Lockpick |  |  |  | Gun |  |  |  | Key
0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 4
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4
4 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 4
4 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 3 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 3 | 4 |  |  |  |  | Idea: |  |  | Scattered rocks all over the place
4 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 4 | [7 empty] | Fast toxics behind you, and you need to reach the other side in time while going through rocks (no need to clear toxic)
4 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 |  |  |  | Queue type: |  |  |  |  | Authored | [11 empty] | Toxic Speed: | [5 empty] | 10
4 | 3 | 0 | 0 | 0 | 0 | 4 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 3 | 4 |  |  |  | Loop/Finite: |  |  |  |  | Loop | [11 empty] | Toxic Spread: | [5 empty] | 9
4 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 |  |  |  | Authored queue: |  |  |  |  | 1 | Axe | [10 empty] | Max Spread: | [5 empty] | 0
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | [8 empty] | 2 | Gun
4 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 4 | [8 empty] | 3 | Braid
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | [8 empty] | 4 | Lockpick
0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | [8 empty] | 5 | Key
4 | 0 | 4 | 3 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 3 | 0 | 4 | 4 | [8 empty] | … | (loop)
0 | 4 | 0 | 4 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 1 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 4 | 4 | 4 | 4 | 0
24x24
0 | 4 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 4 | 0 | 4 |  | Lv7
4 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 4 | 0 |  |  | Main 1-2: "NON PLUS ULTRA"
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
4 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 4 |  |  | Patterns allowed:
0 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 4 | 4 | 3 | 4 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 3 | [10 empty] | Lockpick |  |  |  | Gun |  |  |  | Key |  |  |  | T-shape |  |  |  | Dab |  |  | Queue type: |  |  |  |  | Authored
3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | [5 empty] | Line/Plus sign | [23 empty] | Loop/Finite: |  |  |  |  | Loop
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | [29 empty] | Authored queue: |  |  |  |  | 1 | T-shape
0 | 0 | 0 | 4 | 0 | 0 | 3 | 0 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | [34 empty] | 2 |  |  |  | Dab |  |  | Toxic Speed: |  |  |  | 15
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 0 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | [34 empty] | 3 | Gun | [5 empty] | Toxic Spread: |  |  |  | 10
4 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | [34 empty] | 4 |  |  |  | Key |  |  | Max Spread: |  |  |  | 0
0 | 0 | 0 | 0 | 4 | 3 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | [34 empty] | 5 |  |  |  | Lockpick
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [34 empty] | 6 |  |  |  | Plus |  |  | Counter?
0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 4 | [34 empty] | … | (loop)
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 4
4 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 |  |  |  | Idea: |  |  | Dedicated level for plus sign
4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 3 | 0 | 4 | [7 empty] | You can beat the level without it (go through sides) but much harder
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | [7 empty] | Idea is that either you work your way through the middle and use the Plus sign in the middle, or go around
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | [8 empty] | the "around" road must be more challenging, so that the middle perfectly positioned plus sign feels extra rewarding
4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | [7 empty] | The idea with the queue is the following: first three pieces "set up" the plus sign, but before you receive the plus sign, you still have two other pieces, so that you understand you "need" the plus sign
0 | 4 | 4 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 4 | 4 | 0 | [9 empty] | Otherwise it's too obvious and straightforward
4 | 0 | 4 | 4 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 1 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 4 | 4 | 0 | 0
24x24 | [24 empty] | L8
0 | 4 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 4 | 4 | 0 |  |  | Main 1-3: BOSS BATTLE: "TOXIC REEF"
4 | 4 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 4 | 0
0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 |  |  | Patterns allowed: | [6 empty] | Gun |  |  |  | Boomerang |  |  |  | S-shape |  |  |  | Axe
4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 4 | 0
0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | [27 empty] | Queue type: |  |  |  |  | Authored
4 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 4 | 4 |  |  |  | 2 | [23 empty] | Loop/Finite: |  |  |  |  | Loop
0 | 4 | 0 | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | [27 empty] | Authored queue: |  |  |  |  | 1 | S-shape
4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0 | 0 | 4 | 4 | 0 | [32 empty] | 2 | Gun | [7 empty] | Toxic Speed: |  |  |  | 10
0 | 4 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | [32 empty] | 3 | Boomerang | [7 empty] | Toxic Spread: |  |  |  | 8
0 | 4 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | [32 empty] | 4 | Axe | [7 empty] | Max Spread: |  |  |  | 6
4 | 4 | 3 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | [10 empty] | L-shape/Antenna | [7 empty] | Z-shape/Firework | [13 empty] | 5 | T-Shape
0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 4 | [32 empty] | 6 | Lockpick | [7 empty] | Counter?
0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | [32 empty] | 7 | Antenna
4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | [32 empty] | 8 | S-shape
0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | [32 empty] | 9 | Gun
4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | [32 empty] | 10 | Boomerang
0 | 4 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | [32 empty] | 11 | Axe
4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | [32 empty] | 12 | Firework
0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | [32 empty] | … | (loop)
4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0
4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 |  |  | Idea: |  |  | "Tower defense": straighforward level: fast expanding toxics on one side, you on the other, who will win? (toxic of course)
0 | 4 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 4 | 0 | [6 empty] | Dedicated level for SkullFace and Firework
0 | 4 | 4 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 4 | 4 | 0 |  |  |  |  | Idea is that this level is a battle against a tide rolling over you
4 | 4 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 1 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 4 | 0 |  |  |  |  | Technically, probably worth being careful with the rate of spread
You can either go through the middle (difficult), or use the Antenna or Firework is two specific ponits on the sides that open up the sides entirely (rewarding)
24x24
0 | 0 | 4 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 4 | 0 | 0 | 4 | 0 | 0 |  | L9
0 | 4 | 2 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  | Main 2-1: "UNFOLD ROYALE"
4 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
5 | 5 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  |  | Patterns allowed:
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 |  |  |  |  | Braid |  |  |  | Axe |  |  |  | Boomerang |  |  | S-shape |  |  |  | Dab | [6 empty] | Queue type: |  |  |  | Authored
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | [26 empty] | Loop/Finite: |  |  |  | Loop
4 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Authored queue: |  |  |  | 1 | Axe
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | [30 empty] | 2 | Braid | [7 empty] | Toxic Speed: |  |  |  | 10
0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [30 empty] | 3 | Boomerang | [7 empty] | Toxic Spread: |  |  |  | 8
0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0 | 0 | [30 empty] | 4 | Dab | [7 empty] | Max Spread: |  |  |  | 5
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [30 empty] | 5 | S-shape
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [30 empty] | 6 | Antenna | [7 empty] | Counter?
0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | [6 empty] | L-shape/Antenna | [6 empty] | Line/Plus sign | [16 empty] | 7 | Axe
0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [30 empty] | 8 | Braid
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 1 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | [30 empty] | 9 | Boomerang
0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [30 empty] | 10 | Dab
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | [30 empty] | 11 | S-shape
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | [30 empty] | 12 | Plus
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | [30 empty] | … | (loop)
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0
0 | 0 | 4 | 0 | 0 | 4 | 4 | 0 | 4 | 4 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 4 | 0 | 0 |  |  | Idea: |  |  | Unfold Royale: start the entire perimeter toxic and growing inwards, shrinking =o]
24x24
0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 2 | 5 | 0 |  | L10
0 | 0 | 4 | 4 | 4 | 5 | 5 | 5 | 0 | 4 | 4 | 0 | 4 | 5 | 5 | 5 | 5 | 5 | 4 | 5 | 5 | 5 | 5 | 0 |  |  | Main 2-2: "A MAZE IN TIME"
4 | 4 | 5 | 5 | 5 | 5 | 0 | 5 | 5 | 5 | 5 | 4 | 5 | 5 | 4 | 5 | 4 | 5 | 4 | 5 | 4 | 4 | 5 | 0
5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 4 | 4 | 5 | 4 | 4 | 4 | 5 | 4 | 5 | 4 | 0 |  |  | Patterns allowed: | [6 empty] | Cross | [20 empty] | Queue type: |  |  |  |  | Authored
5 | 4 | 4 | 4 | 4 | 4 | 0 | 4 | 4 | 4 | 4 | 4 | 5 | 0 | 4 | 5 | 5 | 5 | 5 | 5 | 4 | 5 | 4 | 0 | [13 empty] | Just one shape (for controling player movement better) | [16 empty] | Loop/Finite: |  |  |  |  | Loop
5 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 5 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 4 | 5 | 0 | 0 | [30 empty] | Authored queue: |  |  |  |  | 1 | Cross
5 | 4 | 5 | 4 | 4 | 4 | 5 | 4 | 4 | 4 | 5 | 4 | 5 | 0 | 5 | 5 | 5 | 4 | 0 | 4 | 4 | 5 | 4 | 0 | [35 empty] | … | (loop)
5 | 4 | 5 | 4 | 5 | 5 | 5 | 4 | 5 | 4 | 5 | 4 | 5 | 4 | 0 | 4 | 5 | 4 | 0 | 4 | 5 | 5 | 4 | 0
5 | 4 | 5 | 4 | 5 | 5 | 5 | 4 | 4 | 4 | 5 | 4 | 5 | 5 | 5 | 5 | 5 | 4 | 5 | 5 | 5 | 4 | 0 | 0
5 | 4 | 5 | 4 | 4 | 4 | 5 | 4 | 5 | 4 | 5 | 4 | 4 | 4 | 4 | 0 | 5 | 4 | 4 | 4 | 5 | 0 | 0 | 0
5 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 5 | 5 | 5 | 5 | 5 | 4 | 0 | 0
5 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 4 | 4 | 5 | 4 | 4 | 4 | 5 | 4 | 4 | 4 | 4 | 4 | 5 | 4 | 0 | 0 | [30 empty] | Toxic Speed: | [5 empty] | 20
5 | 4 | 5 | 0 | 5 | 5 | 4 | 5 | 4 | 5 | 5 | 5 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 0 | [30 empty] | Toxic Spread: | [5 empty] | 4
5 | 4 | 5 | 4 | 5 | 4 | 4 | 5 | 4 | 4 | 5 | 4 | 4 | 5 | 4 | 4 | 4 | 5 | 4 | 4 | 4 | 5 | 4 | 0 | [30 empty] | Max Spread: | [5 empty] | 0
5 | 4 | 5 | 4 | 5 | 5 | 5 | 5 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 5 | 4 | 5 | 4 | 5 | 4 | 0 |  |  |  |  | Idea: |  |  | Can we make a level with no unfolding?
5 | 5 | 5 | 0 | 4 | 4 | 4 | 5 | 5 | 5 | 0 | 4 | 0 | 5 | 4 | 4 | 4 | 5 | 4 | 5 | 4 | 5 | 4 | 0 | [8 empty] | Like: labyrnth, or racing against expanding toxic (fast one) | [21 empty] | Counter?
0 | 4 | 5 | 5 | 5 | 5 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 4 | 5 | 5 | 5 | 4 | 5 | 4 | 5 | 4 | 0
0 | 4 | 5 | 4 | 0 | 5 | 5 | 5 | 5 | 5 | 0 | 4 | 4 | 5 | 4 | 4 | 4 | 5 | 4 | 4 | 4 | 5 | 4 | 0
0 | 4 | 5 | 4 | 4 | 0 | 4 | 4 | 4 | 5 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0
3 | 4 | 5 | 5 | 5 | 5 | 4 | 4 | 4 | 5 | 4 | 5 | 4 | 4 | 0 | 5 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 0
0 | 0 | 4 | 0 | 4 | 5 | 5 | 4 | 5 | 5 | 4 | 5 | 4 | 5 | 4 | 5 | 4 | 5 | 5 | 5 | 5 | 5 | 4 | 4
0 | 0 | 0 | 0 | 0 | 4 | 5 | 5 | 5 | 4 | 5 | 5 | 4 | 5 | 4 | 5 | 0 | 4 | 4 | 4 | 4 | 5 | 4 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 5 | 5 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 4 | 0
3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 3
24x24
0 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 0 |  | L11
4 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 4 |  |  | Main 2-3: "LOCKDOWN"
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 4
0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 |  |  | Patterns allowed:
4 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0
4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 4 |  |  |  | Key |  |  |  | Cross |  |  |  | Lockpick |  |  |  | T-shape |  |  |  | Braid |  |  |  | Gun
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4
4 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | [29 empty] | Queue type: |  |  |  |  | Authored
0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | [29 empty] | Loop/Finite: |  |  |  |  | Loop | [7 empty] | Toxic Speed: |  |  |  | 15
0 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | [29 empty] | Authored queue: |  |  |  |  | 1 | T-Shape | [6 empty] | Toxic Spread: |  |  |  | 10
4 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | [34 empty] | 2 | Key | [6 empty] | Max Spread: |  |  |  | 0
4 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | [34 empty] | 3 | Cross
3 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 3 | [34 empty] | 4 | Lockpick
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 4 | [34 empty] | 5 | Braid
3 | 4 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 4 | 0 | 3 |  |  | Idea: |  |  | going through tight spaces, | [28 empty] | 6 | Gun
4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | [5 empty] | trying to place pieces in tight places and trying to find the best way to go through | [28 empty] | … | (loop)
4 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | [5 empty] | idea is that this level will require players to carve a path out, trying to go trhough different places
3 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 3
4 | 0 | 4 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 4
3 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
4 | 0 | 0 | 0 | 3 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 3 | 0 | 0 | 4
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 4
3 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 1 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 3
24x24
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 2 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  | L12
0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 0 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Main 2-4: "Key party"
0 | 4 | 4 | 4 | 4 | 0 | 4 | 4 | 0 | 4 | 4 | 4 | 4 | 0 | 4 | 4 | 4 | 5 | 4 | 4 | 4 | 4 | 0 | 0
4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 4 | 0 |  |  | Patterns allowed:
4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 4
4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 5 | 4 |  |  |  | Key
4 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 4 | 3 | 0 | 0 | 0 | 0 | 5 | 4
4 | 0 | 0 | 4 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | [29 empty] | Queue type: |  |  |  |  | Authored
4 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | [29 empty] | Loop/Finite: |  |  |  |  | Loop | [7 empty] | Toxic Speed: |  |  |  | 15
4 | 4 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 4 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 5 | 4 | [29 empty] | Authored queue: |  |  |  |  | 1 | Key | [6 empty] | Toxic Spread: |  |  |  | 10
0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | [34 empty] | … | (loop) | [6 empty] | Max Spread: |  |  |  | 3
0 | 4 | 0 | 0 | 0 | 5 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 4
0 | 0 | 4 | 0 | 0 | 0 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 4 | 4 | 0 | 5 | 4 | 4
0 | 0 | 0 | 4 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 5 | 0 | 0
0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 4 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 5 | 0 | 4 | 0 | 4 | 0 | 0 |  |  | Idea: |  |  | going through tight spaces,
0 | 0 | 3 | 3 | 0 | 4 | 0 | 5 | 0 | 4 | 4 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | 5 | 0 | 4 | 0 | 0 | 0 | [5 empty] | trying to place pieces in tight places and trying to find the best way to go through
0 | 0 | 0 | 3 | 0 | 4 | 0 | 0 | 5 | 5 | 5 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 5 | 4 | 0 | 0 | 0 | 0 | [5 empty] | idea is that this level will require players to carve a path out, trying to go trhough different places
0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 4 | 5 | 5 | 0 | 4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 0 | 0 | 4 | 5 | 5 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 0 | 0 | 5 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 0 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 5 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 5 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 1 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24x36
0 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 0 |  | L12
4 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 4 |  |  | Main 2-5: FINAL BOSS BATTLE: "SHOWDOWN: BOSSBOX"
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 |  |  | Patterns allowed:
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 |  |  |  | Key |  |  |  |  | S-shape |  |  |  |  | Gun |  |  |  |  | Braid |  |  |  |  | Axe |  |  |  | Dab
4 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 4
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | [34 empty] | Queue type: |  |  |  |  | Authored, then random
4 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 3 | [34 empty] | Authored queue: |  |  |  |  | 1 | Key
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | [39 empty] | 2 | S-Shape
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [39 empty] | 3 | Gun
4 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | [39 empty] | 4 | Braid
4 | 0 | 0 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 4 |  |  |  | Worm |  |  |  |  | Cross |  |  |  |  | T-shape |  |  |  |  | Boomerang |  |  |  |  | Lockpick |  |  |  |  | Skullface | [10 empty] | 5 | Skullface
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | [39 empty] | 6 | Axe
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | [39 empty] | 7 | Dab
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [39 empty] | 8 | Worm
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | [39 empty] | 9 | Cross
0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | [39 empty] | 10 | T-Shape
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [39 empty] | 11 | Skullface
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | [39 empty] | 12 | Boomerang
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | [39 empty] | 13 | Lockpick
0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 |  |  |  | Idea: |  |  | Massive Toxic on one side, but you have queue of Tetris | [32 empty] | 14 | Skullface
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | Feel the power of skullface and other Tetris shapes | [31 empty] | … | (full random: any piece from 11 + 4)
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | [7 empty] | All shapes are used
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | [7 empty] | Random list, any shape can come up
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | [34 empty] | Toxic Speed: | [5 empty] | 5
4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Use your skills you acquired, to "unlock" each area | [27 empty] | Toxic Spread: | [5 empty] | 4
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | [34 empty] | Max Spread: | [5 empty] | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | [34 empty] | Counter?
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 4 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
4 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 4
0 | 4 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 1 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 4 | 0

## LvLFeedback
Name | Level | Grade /5 | Feedback
Phil | 0.1 | 5 | Would play again.
Phil | 0.2 | 4 | We should be able to *not* take the short cut. (First piece almost has to be put in the shortcut place.)
Phil | 0.3 | 5
Phil | 0.4 | 5 | Great intro to the toxic spills
Phil | 0.5 | 4 | This level ironically could do with getting a little harder again, but not by much. ;)
Phil | 1.1 | 3 | Good level, with a few annoying rocks, fighting the toxic is a little too easy to fight off. My thought was this level was supposed to reinforce that you don't need to patch the sources to win, but you can get caught up in making the world better and miss the message. I recommend increasing the spread speed, and putting the sources behind rocks to prevent the player from patching them.
Phil | 1.2 | 4 | What's our goal here? To introduce the mega plus piece? If so we need to have it so that you almost can't miss that it's got a situational advantage, I'd recommend changing the queue order to ensure we get it at the right time, and making sure the pieces before lead us right to the perfect placement. I'd also recommend making the shape a little different to ensure we get some deep toxic around the pool to show off super powers.

## Documentation
Level Creation
Level builder how to use:
It can be run from the Grid3 scene if you want to test
When you start the scene you'll need to press the 'Home' key to spawn the level layout
The layout itself is read from a csv file
We can author new levels by creating an Excel sheet and inputting numbers from 0 - 5:
0 - Empty (unset tile)
1 - Start tile
2 - End tile
3 - Magma/Toxic tile
4 - Blocking (rocks) tile
5 - Solid ground (pre-gen island)
If you make any levels you should save them to Assets/Resources/Levels/Lv#.txt
Where # is the level number
Also, yes they need to be .txt files because of Unity reasons
Edit the text file and remove any trailing blank lines
|  |  |  | 0 | Empty (unset tile) |  |  |  | Summary:
|  |  |  | 1 | Start tile |  |  |  | You enter in an excel .csv grid some numbers from 0 to 5 corresponding to tile types
|  |  |  | 2 | End tile |  |  |  | Then save that file into a txt, which transforms that data into comma separated text
|  |  |  | 3 | Magma/Toxic tile |  |  |  | Then, the code for the level builder uses these and creates tiles from them
|  |  |  | 4 | Blocking (rocks) tile
|  |  |  | 5 | Solid ground (pre-gen island)
Level config:
Config file is in Assets\Resources\Levels and int he following format: Lv1.cfg.txt
{ "ToxicSpreadTime": 10, "ToxicSpreadTimeVariation": 2 }
Where:
"ToxicSpreadTime" is in secs
"ToxicSpreadTimeVariation" is the spread of the normal curve, in secs
Setting up environments:
Environments can now be configured from the .cfg file
Set "EnvironmentName" to the name of the environment file to load (Environments must be prefabs in the Resources/Environments directory)
If necessary set "EnvironmentOffsetX", "EnvironmentOffsetY" and "EnvironmentOffsetZ" to offset the environment from origin
See Lv1.cfg.txt for example
Controlling toxic spread:
Toxic spread max distance can be controlled from the .cfg file
Set "MaxSpreadDistance" to the number of tiles spread should go from the source tile.
0 = Unlimited
1+ = number of tiles (radius) out from the centre
examples:
|  | Max spread = 1 |  | Spread |  | Max = 2 | Spread | Max = 3 |  | Spread
|  |  |  | Source |  |  | Source |  |  | Source
Conveyor/Queue how to use:
You need to make a ManualConveyorQueue asset by going to RMB->Create->Scriptable Objects/ManualConveyorQueue and placing shapes you want in that queue.
Atm make sure the type of shape is also added to the Unfold's Shape definitions in the AnimatedPlayer
Then select the NextShapeQueue and drag the newly created asset onto the ConveyorQueue field, and disable randomized
Authored Queue: options
In the hierarchy, "NextShapeQueue" object holds the list
Options are:
Conveyor queue: has the ordered list of objects in your queue
Randomized: randomizes the queue
Loop queue: when queue ends, loop back to item 1 in the queue
You can add a component to the list
Per level ManualConveyorQueue
In Assets/Resources/Levels/ you have conveyor queues named Lv#_Queue (eg Lv1_Queue, Lv5_Queue) which will automatically be loaded when a level gets loaded
New in the ManualConveyorQueue is a checkbox for looping now, since it's on a per level basis.
When a level doesn't have a ManualConveyorQueue next to the level file, it will default back to randomizing
Making a Build for the game
Steam: File -> Build Setting and click Build